## Sheet0
Item id | Depth | Name | Status | Description | Labels | Expected dates | Willem | Rimgaudas | Todor | Tsvetomir | Vytas
190794 | Sprint | Preparation |  |  | Start date: | 28 August 2013 | x | x | x | x | x
190940 | + | Creating identity | Done |  |  |  | x | x | x | x | x
190896 | + | Listing functional & non-functional requirements | Done |  |  |  | x | x | x | x | x
190894 | + | Discussing the project with the formal client | Done |  |  |  | x | x | x | x | x
190892 | + | Creating project plan | Done |  |  |  | x | x | x | x | x
[5 empty] | End date: | 10 September 2013
190897 | Sprint | Design |  |  | Start date: | 11 September 2013
190905 | + | Discussing the current project status | To-do |  |  |  | x |  | c | x |  | Version 1 | Version 2 | Version 3
190904 | + | Website design | Running | design Done
190901 | + | Creating date-base design | To-do |  |  |  |  | c |  |  | x
190900 | + | Normalization (using the list of requirements) and creating data models. | Running | [8 empty] | Creating entities | Discussing which
190899 | + | C# Applications design | Running |  |  |  |  | x | x
[5 empty] | End date: | 19 October 2013 | [5 empty] | List of functional requirement about the programs |  |  | App for entrance | App for camping | Bar application | Application for shops | Application at the stand where you load materials | Application at the end when visitor leaves | application for the organization to inspect the status of the event
190907 | Sprint | Build functionality & Implementation |  |  | Start date: | 20 October 2013
190911 | + | Create .php functionality/ website navigation functionality | To-do |  |  |  | x | x | x | x | x | I don’t know what to put hear think of something :)
190910 | + | Implementing / Creating physical database. | To-do |  |  |  |  | x |  |  | x
190908 | + | Creating C# applications functionality; connect with Database/Website | To-do |  |  |  | x | x | x
[5 empty] | End date: | 22 November 2013
190913 | Sprint | Testing & Debugging |  |  | Start date: | 23 November 2013 | x
190914 | + | Testing the system (with all things connected); Debugging if needed | To-do
[5 empty] | End date: | 14 December 2013
190915 | Sprint | Presentation |  |  | Start date: | 27 January 2014
190916 | + | Preparing final documents and files | To-do
190789 | Sprint | Backlog